GlobGlacier
WP4 progress at SGEU
Eero Rinne,
s0794770@sms.ed.ac.uk
University of Edinburgh
School of GeoSciences
Edinburgh Earth Observatory

---
Project work status (August 2008)
#	Name of deliverable	Date	Status
Phase 1:
1	Requirements Baseline	KO + 3	Done
2 Design Justification File	KO + 5	Done (almost)
3 Technical Specification	KO + 9!	To be written
4 Service Case Description	KO + 9!	To be written
5 Design Definition File	KO + 9!	To be written
6 Acceptance Test Document	KO + 12	To be written
7	Product Validation Protocol	KO + 13	To be written
8	Prototype Product Set (200 WP4 products)	KO + 15	~ 20/200
9	Preliminary Validation and Assessment Report	KO + 15	To be written
Phase 2:	(not begun yet)
10	GlobGlacier products accord. to SCD (800 prod.)	KO + 16-33	0/800
11	GlobGlacier System	KO + 30
12	Promotional DVD	KO + 32
13 Product Validation Report	KO + 35
14	Integration Report	KO + 35

---
Work Packet 4 – elevation change
“Changes in glacier surface elevation will be obtained by differencing gridded
DEMs from two epochs in time (e.g. InSAR, stereo-photogrammetry) and from
time-series of satellite (and partly airborne) altimetry data (e.g. RADAR, LiDAR). Additionally, methods for spatial extrapolation of point measurements to the
entire glacier surface will be developed.”

---
Work behind deliverables
Done so far:
Processing software for IceSat GLAS data → elevation change
Processing software for EnviSAT RA2 data → elevation change
Preliminary sensitivity and error analysis
Point elevation change and error assesment are the two information layers
required to be in WP4 product laid down by SoW.
Todo:
Finalize and optimize GLAS and RA2 scripts
Test on real WP1 and GLIMS outlines in different places
InSAR DEM processing chain – work will begin in September and software will
be ready at spring 2009 when free ASTER DEM:s are due
InSAR DEM:s are required for raster comparison elevation change product

---
IceSat GLAS 06 dataset
Laser altimeter data [1]
Global coverage: 86 N – 86 S
Density of ground tracks increases with latitude
Elevation [h] measurements of land areas
Laser altimeter with ~ 65 m footprint and 170 m spacing between measurements
Precision ~ 15-50 cm depending on the surface slope [2]
15 observation periods so far
first: 20 Feb. to 21 Mar. 2003
last so far: 17 Feb to 21 Mar 2008.
Available for free

---
GlobGlacier processing chain for IceSat data
Extract elevations for area of interest from GLAS06 global product
 (needs lat/lon box as input)
Read data into Matlab
Reproject if necessary
Find crossover points inside outline given by WP1 (accepts shapefile as input)
Average elevations inside 100-500 m radius of crossover points for each
 operation period (or interpolate elevation in exact crossover point)
Filter out bad data points:
3-sigma clipping, too much temporal variation
Calculate trend and standard deviation for elevations at each crossover point
Output is surface elevation [m], elevation trend [m/a] and std. of elevation [m]
 and timespan [a] of measurements inside given outline

---
IceSat GLAS data challenges
IceSat is optimized for large ice sheets with very small or zero surface tilt
91 day repeat orbit makes getting repeat measurement from same place scarce
Spatial averaging problematic due to surface tilt – elevation trend is very
 sensitive to averaging parameters
Using lower level data might provide better filtering tools but is really
 beyond scope of GlobGlacier
Nevertheless IceSat data has been used for studies of smaller ice bodies with
complicated surface geometry – for example Malaspina Glacier, Alaska [3]

---
EnviSAT RA2 (radio altimeter) data
Radio altimeter ~ 10 km footprint
Data available since late 2002 to present
RA2 copes better with land ice surface elevation than RA1 did (that is, does
 not lose lock when retracking surface as easily).
Arctic land areas > 65N (similar dataset for Antarctic areas available later)
Elevation change (dH) at every orbital crossover point where ascending
 and descending track elevations agree
Processed from lower level data by UCL, London

---
GlobGlacier processing chain for RA2 data
Read data into Matlab
Reproject if necessary
Find crossover points inside outline given by WP1
Filter out bad data points
3-sigma clipping, too much temporal variation, something else?
Calculate trend and standard deviation for elevations at each crossover point
Output is surface elevation trend [m/a] and std. of elevation of RA2 orbital
  crossover points inside given outline [m] and measurement timespan [a]

---
Method development area – Devon Ice Cap
Relatively large ice cap (14000 km^2) relatively north (75 N)
 → multiple RA2 and GLAS orbital crossover points
Shape and flow is well documented and an airborne DEM is available [4] [5]
Elevation 0-2000 m.
ASIRAS radio altimeter data from CryoSAT validation experiment campaigns
 available (tools to process this have been made but data has not been yet used.)
Has areas with complicated geometry and a rather simple dome structure
Nice picture of Devon here!
Image: Devon Island from Landsat global mosaic (NASA)

---
Devon Ice Cap elevation trends from GLAS and
RA2 (preliminary results)

---
Point elevation trends - GLAS

---
Point elevation trends - RA2

---
GLAS and RA2 errors

---
Other work on Devon elevation change
From Colgan et. al 2008 [6]: Elevation change of high altitude area of Devon from InSAR
velocity, in situ stake and accumulation measurements – claiming elevation change to be near
zero. Black lines are flight lines of NASA laser altimeter flights Abdlati et. al, 2004 [7].

---
To Be Solved
Need for better data filtering algorithm is apparent – one elevation outlier
 will mess up elevation trend
Should we use spatially averaged or extrapolated IceSat measurements?
How to combine RA2 data using different reference orbits?
How to tackle seasonal variation:
Guess magnitude and phase from other sources?
Fit a sinusoidal curve with 12 month wavelength?
Only use measurements made in certain time of year?
Forget about it?
On some glaciers (suitable orientation, too small for enough orbital crossovers)
 GLAS repeat track processing might be best solution.
Spatial extrapolation of point measurements to the entire glacier surface?
Easy enough if meteorological conditions and accumulation/drainage are
constant over the whole glacier but for example Devon Ice Cap needs
dividing into smaller areas. We need for additional information to do this!

---
DEM generation by InSAR [8]
SGUE has access to archive of ERS-1, ERS-2 and ASAR images suitable
 for DEM creation by InSAR processing
Output is a very high resolution (< 10 m x 10 m) high precision DEM
Usage of IceSAT GLAS measurements as control points will improve accuracy
 and allow DEM creation in areas with no or poor ground control points
InSAR DEM:s will be compared with other raster DEM:s (ASTER, airborne,
 other historic) resulting in elevation change raster
Creating DEM (registering data, error estimation, unwrapping etc.) is time
 consuming manual work.

---
Quick example of an InSAR DEM
ERS1/2 tandem InSAR DEM. 95-96, NE Greenland (K. Briggs, SGUE)

---
Map of SAR scenes available for DEM creation

---
Interaction with other WP's
WP1
Ice cap and glacier outlines
If possible, outlines of basins and drainage areas?
WP3
Need for ASTER DEM:s to compare with InSAR
We will provide DEM:s from InSAR as agreed
We want to pick a common test area to concentrate on in the first stage
(one of the key regions of phase 1, probably) and agree when we have
our DEM:s ready for comparison
WP5
Velocity maps to distinguish subareas (drainage basins, ice flows) to
support elevation change analysis
General
Agree on data format of raster DEM:s and point elevation change products

---
References
[1] Zwally et al: ICESat's laser measurements of polar ice, atmosphere, ocean and land
    Journal of Geodynamics. Vol 34, 2002.
[2] Brenner et al: Precision and Accuracy of Satellite Radar and Laser Altimeter Data Over the
        Continental Ice Sheets
     IEEE Transactions on geoscience and remote sensing, Vol. 45, No. 2, Feb 2005
[3] Sauber et at: Ice elevations and surface change on the Malaspina Glacier, Alaska
     Geophysical research letters, Vol 32, 2005
[4] Dowdeswell et al: Form and flow of the Devon Island Ice Cap, Canadian Arctic.
     Journal of geophysical research - earth surface Vol. 109 Issue: F2, April 2004.
[5] Shepherd et al: Mass balance of Devon Ice Cap, Canadian Arctic.
     Annals of Glaciology vol. 46, 2007
[6] Colgan et al: Is the high elevation region of Devon Ice Cap thickening?
    Journal of Glaciology, Vol 54, No. 186, 2008
[7] Abdlati et al: Elevation changes of ice caps in the Canadian Arctic Archipelago
    Journal of Geophysical Research, Vol 109, 2003
[8] Rosen et al: Synthetic aperture radar interferometry,
    IEEE Proceedings Vol. 88 Issue 3, 2000.